Changes to Capital Works Management Framework28 June 2016

# Amended forms of Contract introduced by Circular 01/16 – Conditions of Contract

| Clause | Details of changes Forms available under http://constructionprocurement.gov.ie/circular-documents/ | PW-CF1 v2.0 22/01/2016 | PW-CF2 v2.0 22/01/2016 | PW-CF3 v2.0 22/01/2016 | PW-CF4 v2.0 22/01/2016 | PW-CF5 v2.0 22/01/2016 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Definition of ‘Adjudication’ added. |  |  |  |  |  |
| 4.10.2(8) | Details of disputes referred to Adjudication to be included in Progress Reports. |  |  |  |  | N/A |
| 11 | ‘Working days’ replaced with ‘days’ throughout. |  |  |  |  |  |
| 11.1.1 | Contractor to submit a ‘Payment Claim Notice’ in the form of an interim statement not later than 5 days after the date the Parties agree to be the Payment Claim Date. |  |  |  |  |  |
| 11.1.1 | Statement given at time of Substantial Completion to be an Interim Statement |  |  |  |  |  |
| 11.1.3 | Within 14 days of receipt of the Payment Claim Notice the Employer’s Representative is to issue response to the payment claim notice, in the form of a certificate. |  |  |  |  |  |
| 11.1.4 | Contractor to issue invoice for an amount due following receipt of response to payment claim notice and the Employer shall pay amount due within 21 days. |  |  |  |  |  |
| 11.3.2 | Contractor to furnish a copy of invoices sent to the employer for sums retained to the Employer’s Representative. |  |  |  |  |  |
| 11.3.3 & 11.3.5 | 10 working days changed to 14 days and 15 working days changed to 21 days |  |  |  |  |  |
| 11.5.4 | 15 working days changed to 21 days and 10 working days changed to 14 days |  |  |  |  |  |
| 11.6.2 | Relevant legislation update to: European Communities (Late Payment in Commercial Transactions) Regulations 2012. |  |  |  |  |  |
| 11.7.4 & 11.7.6 | Relevant legislation update to: Value-Added Tax Consolidation Act, 2010 |  |  |  |  |  |
| 12.3 | Altered to comply with rights of Contractor, under the Construction Contracts Act, 2013, to suspend for failure by the Employer to pay any amount due. |  |  |  |  |  |
| 13.2.10 | Either Party may refer the failure of the other to comply with a binding conciliator’s recommendation to Adjudication, [where the dispute is relating to payment]. |  |  |  |  | Clause 13.1.10 |
| 13.3 | New clause inserted for the effects Adjudication has on contractual dispute resolution procedural options. Arbitration, Jurisdiction, Agent of Service and Continuing Obligations clauses have been renumbered accordingly. |  |  |  |  | Clause 13.2 |

# Amended forms of Contract introduced by Circular 01/16 – Forms of Tender and Schedule

| Schedule | Details of changes Forms available under http://constructionprocurement.gov.ie/circular-documents/ | FTS 1 v2.0 22/01/2016 | FTS2 v2.0 22/01/2016 | FTS3 v2.0 22/01/2016 | FTS4 v2.0 22/01/2016 | FTS5 v2.0 22/01/2016 |
| --- | --- | --- | --- | --- | --- | --- |
| Part1 L | Option to change pay period removed. ‘Monthly’ added in fixed text |  |  |  |  |  |
| Part1 N | ‘Adjudication’ and clause ‘13.4’ added to title |  |  |  |  |  |
| Part1 N | Chairperson of the Panel of Adjudicators added in fixed text as the person to appoint the adjudicator if not agreed by the parties |  |  |  |  |  |
| Part3 C | ‘Adjudication’ and clause ‘13.4’ added to title |  |  |  |  | N/A |

# Amended forms of Contract introduced by Circular 01/16 – Model Forms

| Clause | Details of changes Forms available under http://constructionprocurement.gov.ie/circular-documents/ | MF 1.18 21/03/16 |
| --- | --- | --- |
| 5 | Payment of the Standing Conciliators Fees to be paid as set out in Appendix 2 |  |
| 5 | Discharge of the Fees is subject to compliance by the Standing Conciliator with the provisions of the Agreement and being in possession of a tax clearance certificate. |  |
| 5 | Payment of Fees due shall be made within 30 days of the Standing Conciliator furnishing a valid invoice. |  |
| Appendix 2 | Appendix 2 - Agreed payment terms for fees of the Standing Conciliator - added |  |

# Amended forms of Contract introduced by Circular 01/16 – Guidance Notes

| Section | Details of changes Documents available under http://constructionprocurement.gov.ie/circular-documents/ | Guidance Note GN 1.5 v2.0 22/01/2016 |
| --- | --- | --- |
| Section 1.4 | Tabulated details of Schedule to PW-CF1 to PW-CF5 revised to reflect revisions to Part1 N and Part 3C; |  |
| Section 1.5 | Tabulated details of Schedule to PW-CF6 revised to reflect introduction of clause 4.3 and 15.3; |  |
| Section 1.6 | Tabulated details of Schedule to PW-CF7 revised to reflect introduction of clause 16.3; |  |
| Section 1.7 | Tabulated details of Schedule 11 to PW-CF10 revised to reflect introduction of clause 4. |  |
| Section 1.8 | Tabulated details of Schedule to PW-CF11 revised to reflect clause 11.1, 11.2 14.2 and introduction of clause 14.3. |  |
| Section | Details of changes Documents available under http://constructionprocurement.gov.ie/circular-documents/ | Guidance Note GN 1.5.3 v1.1 21/03/2016 |
| Section 4.3 | Revised test to allow for revision to payment clause terms in all forms of Contract. Reference to ‘Payment Claim Notice’ and ‘Payment Claim Date’ added |  |
| Section 4.4 | Title altered to allow for revised payment cause terms in all forms of Contract. Reference to ‘Response to Payment Claim Notice’ added |  |
| Section | Details of changes Documents available under http://constructionprocurement.gov.ie/circular-documents/ | Guidance Note GN 3.1.1 v1.0 22/01/2016 |
| Forward | Note added to table: All contracts entered into on or after the 25th of July 2016 are subject to statutory adjudication under the Construction Contracts Act, 2013 |  |
| Section 1.7 | Section 1.7 added detailing the effect of Adjudication under the Construction Contracts Act 2013 on the dispute management procedure |  |
| Section 2.2 | Note amended to reflect contractual requirement to complete Dispute Management Procedure where such a referral occurs prior to referral of same dispute to conciliation |  |
| Section 2.7 | New section 2.7 added detailing the effect of Adjudication under the Construction Contracts Act 2013 on conciliation. Standing Conciliator and Neutral Advisor sections renumbered accordingly. |  |
| Section 3.1 | New section 3.1 added detailing Parties rights to Adjudication process under the Construction Contracts Act, 2013. Reference to Act included. Arbitration and The Courts section renumbered accordingly. |  |
| Section 4. | Note added to flow diagrams: All contracts entered into on or after the 25th of July 2016 are subject to statutory adjudication under the Construction Contracts Act, 2013 |  |

28 June 2016