Project Review on Completion Guidance Notes                                                                                                                                                                                                        Document Reference GN 4.1 V.1.0.                                                                                                                                                                                    28 July 2009

© 2009 Department of Finance

Published by: Department of Finance
Government Buildings
Upper Merrion Street
Dublin 2.

This document is not to be taken as a legal interpretation of the contracts or of the provisions governing public procurement. All parties must rely exclusively on their own skills and judgment or upon those of their advisors when making use of this document. The Government Construction Contracts Committee (GCCC), the National Public Procurement Policy Unit (NPPPU) and the Department of Finance and any other contributor to this guidance note do not assume any liability to anyone for any loss or damage caused by any error or omission, whether such error or omission is the result of negligence or any other cause. Any and all such liability is disclaimed.

#### Contents

1: Overview of Project Review on Completion	14

1.1 Introduction	15

1.2 Success Criteria and Measurement	16

1.3 Project Evaluation	18

1.4 Performance Evaluation	19

2: Performance Evaluation	20

2.1 Introduction	20

2.2 Performance – Works Contractors	21

2.3 Performance - Consultants	23

3: Analysis of Outturn Costs	26

3.1 Introduction	26

3.2 Collecting and Profiling Cost Data	27

3.3 Analysis of Additional Construction Cost	29

3.4 Standard Approach to Cost Comparison	30

4: Other Essential Review Activities	31

4.1 Introduction	31

4.2 Design Review	32

4.3 Analysis of Additional Construction Time	33

4.4 Value Management and Risk Management Review	34

Appendix: Template for End-of-Project Report Documents	35

#### Foreword

| Purpose of this document | This document is one of a number of guidance notes aimed at facilitating the implementation of the Government’s reforms in construction procurement. Its purpose is to give an overview of Project Review on Completion which is the final stage of the management of capital works projects. Project Review on Completion covers a range of activities that have as their end goal the comprehensive description of the end of project status for the benefit of future projects. These activities are conducted in a systematic, rigorous and formal manner, and lead to defined outcomes in the form of the End-of-Project Report. This document is also intended as a strategic resource for the wider public sector. |
| --- | --- |

| Audience for this document | This document is intended primarily for the guidance of Sponsoring Agencies embarking on traditional and design-and-build projects. It should be promoted by Sanctioning Authorities as best practice for Sponsoring Agencies to follow at the Project Review on Completion stage when assessing the results of the project. While many of the principles in this document apply equally to projects that are to be financed through Public-Private Partnerships, the planning of such projects is outside the scope of this guidance note. |
| --- | --- |

| References in this document | Throughout this document references are made to other documents, including other guidance notes. These references should be understood as referring to the most up to date version in each case. |
| --- | --- |

Continued on next page

#### Foreword, Continued

| What is the Capital Works Management Framework | The Capital Works Management Framework (CWMF) is a structure that has been developed to deliver the Government’s objectives in relation to public sector construction procurement reform. It consists of a suite of best practice guidance, standard contracts and generic template documents that form four pillars that support the Framework; the pillars are: A suite of standard forms of construction contracts and associated model forms, dispute resolution rules, model invitations to tender, forms of tender and schedules; The standard conditions of engagement for consultants, dispute resolution rules, model invitations to tender, forms of tender and schedules; Standard templates to record cost planning and control information; and for suitability assessment; and Extensive guidance notes covering the various activities in a project delivery process. |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| What is the Capital Works Management Framework (continued) | The content of the four pillars is outlined below. The constituent documents are coded according to the following scheme: Code Description Code Description PW-CF Public Works Contract Form COE Standard Conditions of Engagement MF Model Form GN Guidance Note AR Arbitration Rules CO Cost Planning / Control Form ITTS Invitation To Tender, Services ITTW Invitation To Tender, Works QC Questionnaire: Suitability Assessment for Service Provider QW Questionnaire: Suitability Assessment for Works Contractor FTS Form of Tender and Schedule GL Glossary WE Data on Weather Event |
| --- | --- |

| CWMF Pillar 1 | Public Works Contracts Contracts, Model Forms, Arbitration Rules, Invitations to Tender (works), and Forms of Tender & Schedules (works) Contracts PW-CF1 Public Works Contract for Building Works designed by the Employer PW-CF2 Public Works Contract for Building Works designed by the Contractor PW-CF3 Public Works Contract for Civil Engineering Works designed by the Employer PW-CF4 Public Works Contract for Civil Engineering Works designed by the Contractor PW-CF5 Public Works Contract for Minor Building and Civil Engineering works designed by the Employer PW-CF6 Public Works Short Form of Contract PW-CF7 Public Works Investigation Contract PW-CF8 Public Works Short Form of Investigation Contract PW-CF9 Public Works Framework Agreement Weather Event WE 1.0 Met Éireann’s calculations of Weather Events |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| CWMF Pillar 1 (continued) | Model Forms MF 1.0 Model Forms (compendium of all model forms) MF 1.1 Bid Bond MF 1.2 Letter to Apparently Unsuccessful Tenderer MF 1.3 Letter of Intent MF 1.4 Letter of Acceptance MF 1.5 Letter to Tenderers Notifying Award MF 1.6 Performance Bond MF 1.7 Parent Company Guarantee MF 1.8 Novation and Guarantee Agreement MF 1.9 Novation Agreement MF 1.10 Appointment of Project Supervisor MF 1.11 Professional Indemnity Insurance Certificate MF 1.12 Collateral Warranty MF 1.13 Rates of Pay and Conditions of Employment Certificate MF 1.14 Bond – Unfixed Works Items MF 1.15 Retention Bond MF 1.16 Appointment of Conciliator MF 1.17 Bond – Conciliator’s Recommendation Arbitration Rules AR 1.0 Arbitration Rules Invitations to Tender (works) ITTW 1 Invitation to Tender for Works, Restricted Procedure ITTW 2 Invitation to Tender for Works, Open Procedure ITTW 3 Invitation to Tender, Investigation Contract under an Open Procedure Forms of Tender and Schedules FTS 1 Form of Tender and Schedule: Public Works Contract for Building Works designed by the Employer FTS 2 Form of Tender and Schedule: Public Works Contract for Building Works designed by the Contractor FTS 3 Form of Tender and Schedule: Public Works Contract for Civil Engineering Works designed by the Employer FTS 4 Form of Tender and Schedule: Public Works Contract for Civil Engineering Works designed by the Contractor FTS 5 Form of Tender and Schedule: Public Works Contract for Minor Building and Civil Engineering Works designed by the Employer FTS 6 Form of Tender and Schedule: Public Works Short Form of Contract FTS 7 Form of Tender and Schedule: Public Works Investigation Contract FTS 8 Form of Tender and Schedule: Public Works Short Form of Investigation Contract |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| CWMF Pillar 2 | Standard Conditions Standard Conditions of Engagement, Arbitration Rules, Invitations to Tender (services), and Forms of Tender & Schedules (services). Standard Conditions COE 1 Standard Conditions of Engagement for Consultancy Services (Technical) COE 2 Standard Conditions of Engagement for Archaeology Services Arbitration Rules AR 1.0 Arbitration Rules Invitations to Tender (services) ITTS 1 Invitation to Tender for Services, Restricted Procedure ITTS 2 Invitation to Tender for Services, Open Procedure Forms of Tender & Schedule (services) FTS 9 Form of Tender and Schedule, Consultancy Services (Technical) FTS 10 Form of Tender and Schedule, Archaeology Services |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| CWMF Pillar 3 | Cost Planning & Control/ Suitability Assessment Cost Control & Planning Forms; and Suitability Assessment Forms for works and services. Cost Planning & Control Forms CO 1 How to Use the Costing Document (Building Works) Template CO 1.1 Costing Document (Building Works) CO 2 How to Use the Costing Document (Civil Engineering Works) Template CO 2.1 Costing Document (Civil Engineering Works, Roads) CO 2.2 Costing Document (Civil Engineering Works, Water Sector) CO 2.3 Costing Document (Civil Engineering Works, Marine) Suitability Questionnaires (works) QW 1 Questionnaire: Suitability Assessment for Works Contractor, Restricted Procedure QW 2 Questionnaire: Suitability Assessment for Works Contractor, Open Procedure QW 3 Questionnaire: Suitability Assessment for Works Specialist for specialist area Suitability Questionnaires (services) QC 1 Questionnaire: Suitability Assessment for Service Provider, Restricted Procedure QC 2 Questionnaire: Suitability Assessment for Service Provider, Open Procedure QC 3 Questionnaire: Suitability Assessment for Service Provider, Independent PSDP QC 4 Questionnaire: Suitability Assessment for Service Provider, Independent PSCS |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| CWMF Pillar 4 | Guidance Notes Guidance Notes GN 1.0 Introduction to the Capital Works Management Framework GN 1.1 Project Management GN 1.2 Project Definition and Development of the Definitive Project Brief GN 1.3 Budget Development GN 1.4 Procurement and Contract Strategy for Public Works Contracts GN 1.5 Public Works Contracts GN 1.6 Procurement Process for Consultancy Services (Technical) GN 1.6.1 Suitability Assessment of Construction Service Providers, Restricted Procedure GN 1.6.2 Suitability Assessment of Construction Service Providers, Open Procedure GN 1.7 Standard Conditions of Engagement, Guidance Note and Sample Schedules GN 2.1 Design Development Process GN 2.2 Planning and Control of Capital Costs GN 2.3 Procurement Process for Works Contractors GN 2.3.1 Suitability Assessment of Works Contractors, Restricted Procedure GN 2.3.2 Suitability Assessment of Works Contractors, Open Procedure GN 3.1 Implementation Process GN 4.1 Project Review Glossary GL 1.0 Glossary |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| Stages in capital works management | The four major stages in the delivery life cycle of a public works project are set out in the Department of Finance’s Guidelines for the Appraisal and Management of Capital Expenditure Proposals in the Public Sector (February 2005). The four stages are: |
| --- | --- |

|  | Stage | What happens |
| --- | --- | --- |
|  | 1. Appraisal | The needs are identified, the broad parameters of a solution are agreed, and a decision-in-principle is made to proceed. |
| Capital Works Management Framework | 2. Planning | The needs are quantified and assumptions verified, the desired outputs are specified, and the solution is designed. |
|  | 3. Implementation | The solution is constructed. |
|  | 4. Project review | An assessment is carried out of how successfully the delivered solution addresses the needs. |

Continued on next page

Foreword, Continued, Continued

| Strategic Objectives of the CWMF | The strategic objectives of the Government’s Capital Works Management Framework are to ensure: Greater cost certainty at contract award stage; Better value for money at all stages during project delivery, particularly at handover stage; and More efficient end-user delivery. Provided there is a comprehensive definition of the Client’s requirements in terms of output specifications, and adequate pre-tender detail design input (in the cast of traditional contracts), the new public works contracts will enable the key objectives outlined above be achieved. The degree to which output specifications and the pre-tender detailed design input is developed is determined by the following guiding principles which underpin the new contracts: To ensure as far as practicable that the accepted tender prices and the final outturn costs are the same; and To allocate risk so that there is optimal transfer of risk to the Contractor. The public sector Client or is called ‘the Employer’ in the new public works contracts. The achievement of optimal risk transfer is dependent on the Employer providing complete and detailed information in the tender documentation: For design-and-build projects, the Employer must provide detailed output specifications; and For traditional projects, the Employer must provide comprehensive input designs and specifications Then in responding to an invitation to tender, prospective contractors can assess the impact of the risks being transferred and build the costs of such risks into their tender price. |
| --- | --- |

Continued on next page

Foreword, Continued, Continued

| Content | This document is divided into three chapters and an appendix, as follows: |
| --- | --- |

| Chapter | See Page |
| --- | --- |
| 1. Overview of Project Review on Completion Presents an overview of Project Review on Completion planning and the activities involved. | 15 |
| 2. Performance Evaluation Outlines how assessments of the Works Contractors and the Consultants are carried out and recorded. | 20 |
| 3. Analysis of Outturn Costs Consists of Analysis of Collecting & Profiling Cost Data, Analysis of Additional Construction Cast and Standards & Templates | 24 |
| 4: Other Essential Review Activities Outlines other reviews that are necessary: Design Review, Analysis of Outturn Costs and Value and Risk Management Reviews. | 31 |
| Appendix: Template for End-of-Project Report Documents Presents a template that practitioners can use to develop an End-of-Project Report | 35 |

| Project Stages | Capital Works Management Framework |
| --- | --- |
| Appraisal |  | Main Project Processes |
| Approval in Principle |  | Project Management | Design Activities (Building) | Design Activities (Civil Eng.) | Cost Control Activities | Risk and Value Management | Documents for Approval |
| Stage 1 Planning Initial | Stage (i) Feasibility Study / Preliminary Report | Manage outputs: Project Definition (through 16 No overall parameters) Manage technical experts’ appointment (if required) | Conduct Feasibility Studies Develop Definitive Project Brief Appoint technical experts (if required) Appoint PSDP (if required) | Conduct Preliminary Report Conduct design studies Develop Definitive Project Brief Appoint technical experts (if required) Appoint PSDP (if required) | Conduct cost assessment of Feasibility Studies / Preliminary Report (capital and maintenance costs) | VM: Confirm strategic functional performance Review Feasibility Studies / Preliminary Report options Identify VM strategies Develop functional performance model | Project Management Structure Preliminary Project Brief Preliminary Output Specification Feasibility Study and Cost Plan Design Brief Final Output Specification Definitive Project Brief Project Execution Plan Risk Management Plan |
|  |  |  |  |  |  | RM: Identify and assess risk relating to the Project Execution Plan Develop high-level Risk Management Plan |  |
|  | Stage (ii) Design | Project Review 1: Confirm approval for design expenditure (Report to Sanctioning Authority and await approval prior to proceeding) |
|  |  | Manage procurement strategy Manage design consultant appointment Manage assessment of output requirements | Appoint Design Team / Design Team Leader Assess output requirements | Appoint Design Team / Lead Consultant Develop design standards Assess output requirements | Check / assess budget | VM: Consider VM in relation to procurement strategy | Definitive Procurement Strategy Contract Type Proposal Project Team Selection Report |
|  |  |  |  |  |  | RM: Identify risk in relation to procurement Agree risk allocation |  |
| Stage 2 Planning Developed |  | Project Review 2: Confirm requirements; review procurement strategy ( C ertify compliance to Sanctioning Authority; and proceed after agreed period provided no queries / hold from Sanctioning Authority) |
|  |  | Manage Outline Design process | Develop Outline Sketch Scheme Appoint PSDP (if not appointed earlier) | Develop Preliminary Planning Appoint PSDP (if not appointed earlier) | Develop Outline Cost Plan | VM: Consider VM in relation to Outline Sketch Scheme / Preliminary Planning | Outline Sketch Scheme (Building) Preliminary Planning drawings (C. Eng.) Outline Cost Plan |
|  |  |  |  |  |  | RM: Consider RM in relation to Outline Sketch Scheme |  |
|  |  | Project Review 3: Assess project design and Outline Cost Plan ( Certify compliance to Sanctioning Authority; and proceed after agreed period provided no queries / hold from Sanctioning Authority) |
|  |  | Manage Developed Design process Manage procurement process | Develop Developed Sketch Scheme Prepare submission for statutory approval | Continue Preliminary Planning Prepare submission for statutory approval | Develop Developed Cost Plan Develop Whole Life Cost Appraisal | VM: Carry out value engineering Assess buildability of the design Consider VM in relation to Detailed Sketch Scheme | Developed Sketch Scheme Developed Cost Plan Statutory Approval Submission |
|  |  |  |  |  |  | RM: Identify residual risks Consider RM in relation to Detailed Sketch Scheme Suitability assessment of contractors |  |
|  |  | Project Review 4: Assess project prior to statutory approval (Report to Sanctioning Authority and await approval prior to proceeding) |
|  |  | Manage statutory submission process | Submit for statutory approval Review statutory approval outcome | Submit for statutory approval Review statutory approval outcome | Review Developed Cost Plan | VM: Review any planning conditions for value management impact. | Developed Cost Plan (reviewed) |
|  |  |  |  |  |  | RM: Review any planning conditions for risk impact. |  |
|  |  | Project Review 5: Assess outcome from statutory approval ( Certify compliance to Sanctioning Authority; and proceed after agreed period provided no queries / hold from Sanctioning Authority) |
|  | Stage (iii) Tender | Manage the Detailed Design Process | Develop Detailed Design (not design-and-build) Prepare tender documents | Develop Detailed Planning (Design) (not design-and-build) Prepare tender documents | Conduct Detailed and Pre-Tender Cost Checks and Whole Life Cost Update in advance of preparing tender documents | VM: Review suitability assessment of contractors for VM potential | Tender Documentation Detailed Pre-tender Cost Check Whole Life Cost Update Contractor List Selection |
|  |  |  |  |  |  | RM: Review suitability assessment of contractors for risk impact |  |
|  |  | Project Review 6: Approve detailed design solution; review pre-tender cost check; review risk (Report to Sanctioning Authority and await approval prior to proceeding) |
|  |  | Manage the Tender Process | Issue tender documents Assess tender returns Recommend successful tenderer | Issue tender documents Assess tender returns Recommend successful tenderer | Develop Tender Cost Analysis Develop Tender Report | VM: Assess tender returns for VM potential | Tender Assessment Criteria Tender Analysis And Report Contractor Recommendation |
|  |  |  |  |  |  | RM: Assess tender returns for risk impact |  |
|  |  | Project Review 7: Review tender returns in advance of awarding the contract (Report to Sanctioning Authority and await approval prior to proceeding) |
| Stage 3 Implementation | Stages (iv) Construction & (v) (v) Handover | Manage the implementation / construction process Manage change control Manage contract | Develop Detailed Design (Design and Build) Implement design | Develop Detailed Planning (Design and Build) Implement design | Manage change control for costs Prepare final account | VM: Carry out value engineering (for design and build projects only) | Various contract management reports |
|  |  |  |  |  |  | RM: Manage residual risk Manage construction risk |  |
| Stage 4 Review | Manage the Project Review on Completion | Conduct design review | Conduct design review | Develop Analysis of Outturn Cost | VM: Evaluate value achieved | Project Outturn Review |
|  |  |  |  |  | RM: Evaluate the risk management and risk mitigation process Consider operational risk reviews |  |

### 1. Overview of Project Review on Completion

#### 1.1 Introduction

| Importance of project definition | Project definition is the single most important exercise in the design process; and when clear project objectives have been set, the basis for a Project Review on Completion can easily be established. The importance of the role of the project definition is outlined in Project Definition and Development of the Definitive Project Brief (GN1.2). |
| --- | --- |

| Benefits of good planning | Good planning takes time and effort, but brings significant benefits, as outlined in Project Management (GN1.1). The basis for a successful Project Review on Completion is laid in the course of project management from the beginning of a project. Plans for Project Review on Completion should be documented in the Project Execution Plan – see the sample in Appendix A of Project Management (GN1.1). The efficiency of the Project Review on Completion will be greatly enhanced by the quality of the communications plan and records kept throughout the project. Commitment to achieving continuous improvement is also important as outlined in Chapter 8 of Project Management (GN1.1). This chapter presents an overview of Project Review on Completion planning and the activities it involves. |
| --- | --- |

| Topic | See Page |
| --- | --- |
| 1.2 Success Criteria, Measurement and Reporting Outlines how a project’s success criteria, measurements and end-of- project reporting requirements are defined | 16 |
| 1.3 Project Evaluation Presents an overview of the activities involved in performance evaluation of the project and feedback of project participants and shareholders after project completion. | 18 |
| 1.4 Performance Evaluation Outlines how the assessment of client, contractor and consultant performance should be carried out. | 19 |

#### 1.2 Success Criteria and Measurement

| Overall objectives | A fundamental aim of the Capital Works Management Framework is to achieve continuous performance improvement, both within projects, and from one project to the next. Fundamental to this objective is a review procedure that can: Measure performance in capital projects; Determine where improvements in effectiveness, efficiency and quality are required; and Record lessons for future projects. |
| --- | --- |

| Defining success criteria | It is essential that a project’s success criteria are clearly defined and agreed on at the beginning of the project. The Project Coordinator or Project Manager must facilitate this. The criteria for success can be defined through: Business objectives; Technical performance / requirements; and Measurable key performance indicators such as cost, time, quality, experience etc. An early value management workshop (or something similar), should be used to establish these criteria, and should be encouraged as a way of obtaining commitment and agreement from all parties. The success criteria should be incorporated into the Project Execution Plan (PEP) and developed through project definition and the Definitive Project Brief. |
| --- | --- |

| Measuring Success Criteria | Success criteria must be measurable, and the measurement and method of measurement must be stated. Quantitative performance measurements include: Cost outcome (budget predictability); Number of defects (construction quality) ; and Accident number, frequency and severity (Health and Safety). Client satisfaction can also be measured in terms of service and product. User satisfaction measurements can be devised in terms of ‘fitness for purpose’. Success criteria are not the same as acceptance criteria which are used to gauge acceptance of completed product at project handover. |
| --- | --- |

Continued on next page

1.2 Success Criteria and Measurement, Continued

| End-of-project report | The PEP includes a communications plan which details all of the project reporting requirements, reviews and meetings; including those associated with Project Review on Completion. The end-of-project report usually summarises the Project Review on Completion and involves the following tasks: Reviewing project performance against the objectives and success criteria detailed in the Project Brief; Reviewing project performance in relation to the planned time and cost; Reviewing the status of any outstanding issues and recommending follow-on actions; Assessing the positive and negative impact of approved changes; Reviewing the Lessons Learned Log and considering what can be done differently on future projects; Referencing any other documentation resulting from the end of project review procedure – for example, design review, analysis of outturn costs, contract performance reviews, and value and risk management reviews. |
| --- | --- |

| Timing, Participation and Format | The Sanctioning Authority should request the Sponsoring Agency to conduct the Project Review on Completion within 12 months of project completion. It is essential to hold the Project Review on Completion soon after the project is closed so that detailed information is not lost or forgotten. All major shareholders should be represented. The review may take the form of questionnaires, workshops and reports on specific areas (for example, Design), but it should be summarised in the End-of-Project Report. |
| --- | --- |

#### 1.3 Project Evaluation

| Project Evaluation and Feedback | Effective project management (including managing improvement within organisations and across programmes), involves performance evaluation of the project and feedback of project participants both during the project and after project completion. Benchmarking Benchmarking is a management tool to help clients and supplier organisations understand how their performance compares to that of their peers and to drive improvements in processes and outputs. Looking outwards Clients and project teams should be outward looking, recognising that there is much to gain from sharing experiences, comparing performances or using innovative approaches to solving a problem. Projects within a programme Where an organisation has a programme of similar projects, there should be mechanisms in place to help drive continuous improvement from one project to the next. |
| --- | --- |

| Project parameters | There are sixteen project parameters included in the Definitive Project Brief (refer to Project Definition and Development of the Definitive Project Brief, GN1.2). Any or all of these parameters may be used as a basis for project evaluation. |
| --- | --- |

#### 1.4 Performance Evaluation

| Performance measurement of individual parties | As well as measuring overall project performance, the performance of each party should be measured. The purpose of measuring individual performance is to facilitate improved performance in the future, not to berate a party for poor performance or to allocate blame for project failure. |
| --- | --- |

| Client performance | Client bodies also need to measure their own performance and use benchmarking against other clients, to identify areas for improvement. |
| --- | --- |

| Contract performance | All works contractors and consultants should be assessed in accordance with the performance and timeframe details contained in their contract. These assessments are standardised for ease of comparison and may subsequently be used as reference material in relation to suitability assessment of the contractor for future projects. |
| --- | --- |

### 2. Performance Evaluation

#### 2.1 Introduction

| Introduction | This chapter covers the two main types of performance evaluation associated with public works and service contracts. |
| --- | --- |

| Topic | See Page |
| --- | --- |
| 2.2 Performance - Contractors Describes how to assess the performance of Works Contractors at end-of-project | 21 |
| 2.3 Performance - Consultants Describes how to assess the performance of Consultants at end-of-project | 23 |

#### 2.2 Performance – Works Contractors

| Introduction | At the end of the Defects Period as stated in Schedule part 1I and in accordance with Clause 8.6 of PW-CF1 to PW-CF5, the Contractor’s performance should be assessed by the Contracting Authority. The performance assessment process must be in compliance with Article 48 of Directive 2004/18/EC and Regulation 57 of SI No 329 of 2006 European Communities (Award of Public Authorities Contracts) Regulations 2006 and Article 54 of Directive 2004/17/EC and Regulation 56 of SI No 50 of 2007 European Communities (Award of Contracts by Utility Undertakings) Regulations 2007. |
| --- | --- |

| End-of-Project Assessment | The areas under which the performance assessment may be conducted in accordance with the foregoing Directives are: |
| --- | --- |
| Condition | Description |
| 1 | Whether the project was carried out in accordance with the rules of the relevant trade and was properly completed. Properly completed can mean any or all of the following: Quality Were all defects rectified? Was the facility constructed to specification? Were competent tradesmen/skilled workers employer to carry out the work? Were specialist works completed properly? Time Was the project delivered on time Were liquidated damages under sub-clause 9.8 of PW-CF1 to PW-CF5 instituted? Cooperation Did the contractor and his personnel (including Specialists) support reciprocal co-operation for the Contract purposes as specified under sub-clause 4.1 of PW-CF1 to PW-CF5? Programme Was the programme kept up to date as required by sub-clause 4.9 of PW-CF1 to PW-CF5? Communications Were all communications with the contractor and his personnel interpreted purposefully, having regard to the Contract’s purposes as required by sub-clause 4.14 of PW-CF1 to PW-CF5? |

|  | Note: The references above to clauses in PW-CF1 to PW-CF5 does not mean that such assessment should not also be required for projects where the Short Form (PW-CF6) or the Investigation Contracts (PW-CF7 and PW-CF8) are used.. |
| --- | --- |

Continued on next page

2.2 Performance – Works Contractors, Continued

| End-of-Project Assessment (continued) |
| --- |
| Condition | Description |
| 2 | The effectiveness of those (either in-house of outsourced) with responsibility of carrying out quality control. |
| 3 | The effectiveness and technical skills of management of both the contractor and the contractor’s personnel who have acceptable educational and professional qualifications and experience to construct the works. |
| 4 | The effectiveness of the manpower resource employed on the project to construct the works |
| 5 | The effectiveness of the plant engaged on the project and length of time it was engaged to construct the works. |

|  | The end-of-project review should include a commentary on each of the five conditions above so that this information is available for future reference by the Contracting Authority where a new project is being put out to tender. |
| --- | --- |

Note: Comments on conditions 2 to 5 above are for the Contracting Authority’s own use. Comments on condition 1 should be included in a Certificate of Satisfactory Execution and may be shared with third parties (i.e. other Contracting Authorities) provided permission from the contractor is obtained beforehand (see below for details).

| Suitability Assessment prior to new project | The assessment of the contractor’s performance at the end of a project may subsequently form the basis of a response to certain suitability assessment criteria for future projects. Such an assessment may be used to determine if the contractor meets the standard required to be considered further (to participate in tender competition in the case of a restricted procedure), or to have its tender submission moved forward to the tender evaluation stage (in case of an open procedure). Requirements in relation to condition 1 on page 21 are either : included in the standard Certificate of Satisfactory Execution form which is supplied in an appendix to the Suitability Assessment Questionnaire; or may be included under the criterion 3.4.c at ‘CA Entry: supplementary requirements (if any) in relation to this criterion’ and responded to by the applicant / candidate filling in the reply to the requirements in the Certificate of Satisfactory Execution before submission. |
| --- | --- |

#### 2.3 Performance - Consultants

| Introduction | At the end of the Total Performance Period in Schedule A and in accordance with sub-clause 4.6 of the Standard Conditions of Engagement for Consultancy Services (Technical) (COE 1) the consultant’s performance should be assessed by the Contracting Authority. The consultant will be aware from the provision in sub-clause 2(5) of the Standard Conditions that this can happen. This assessment should be carried out on all consultants engaged in providing technical services on a project. The performance assessment process must be in compliance with the following: Article 48 of Directive 2004/18/EC; Regulation 57 of SI No 329 of 2006 European Communities (Award of Public Authorities Contracts) Regulations 2006; Article 54 of Directive 2004/17/EC; and Regulation 56 of SI No 50 of 2007 European Communities (Award of Contracts by Utility Undertakings) Regulations 2007. |
| --- | --- |

| End-of-Project Assessment | The headings under which the performance assessment may be conducted in accordance with the foregoing Directives are: |
| --- | --- |
| Condition | Description |
| 1 | Evidence of how the services provided addressed issues such as the following: Quality The level of input of technical and intellectual skills that the consultant provided during the Planning and Implementation stages of the project. Time The degree of adherence to the Performance Periods for delivery of service from ‘permission to start’ as set out in the Schedule B Stage Technical Services of the Standard Conditions (COE 1). Cooperation Whether the consultant supported reciprocal co-operation for the Contract purposes as specified under clause 8 of the Conditions of Engagement. Communications Whether all communications with the consultant were interpreted purposefully, having regard to the Contract’s purposes as required by clause 6 of the Standard Conditions (COE 1). |

|  | Note: In addition to the foregoing the review should also under this heading provide information on the (sums) value of the fees, the date and the recipient of the service |
| --- | --- |

Continued on next page

2.3 Performance - Consultants, Continued

| End-of-Project Assessment (continued) |
| --- |
| Condition | Description |
| 2 | The effectiveness of those (either in-house or outsourced) with responsibility of carrying quality control. |
| 3 | The effectiveness and technical skills of management of the consultant with acceptable educational and professional qualifications and experience to deliver the service. |
| 4 | The effectiveness of the manpower resource employed to deliver the service. |
| 5 | The effectiveness of the technical equipment engaged on the project and length of time it was engaged to deliver the service. |
| 6 | In the case of a dispute the robustness of the case and supporting documentation defending the case |

|  | The end-of-project review should include a commentary on each of the five conditions above so that this information is available for future reference by the Contracting Authority where a new project is being put out to tender. |
| --- | --- |

Note: Comments on conditions 2 to 5 above are for the Contracting Authority’s own use. Comments on condition 1 should be included in a Certificate of Satisfactory Execution and may be shared with third parties (i.e. other Contracting Authorities) provided permission from the consultant is obtained beforehand (see below for details).

| Suitability Assessment prior to new project | The assessment of the consultant’s performance at the end of a project may subsequently form the basis of a response to certain suitability assessment criteria for future projects. Such an assessment may be used to determine if the consultant meets the standard required to be considered further (to participate in tender competition in the case of a restricted procedure), or to have its tender submission moved forward to the tender evaluation stage (in case of an open procedure). Requirements in relation to condition 1 on page 21 are either : included in the standard Certificate of Satisfactory Execution form which is supplied in an appendix to the Suitability Assessment Questionnaire; or may be included under the criterion 3.4.c at ‘CA Entry: supplementary requirements (if any) in relation to this criterion’ and responded to by the applicant / candidate filling in the reply to the requirements in the Certificate of Satisfactory Execution before submission. |
| --- | --- |

### 3: Analysis of Outturn Costs

#### 3.1 Introduction

| Introduction | This chapter covers analysis of outturn costs from the main contract award through to project completion. |
| --- | --- |

| Topic | See Page |
| --- | --- |
| 3.2 Collecting and Profiling Cost Data Describes techniques for the collection and use of cost data. | 27 |
| 3.3 Analysis of Additional Construction Cost Describes what actual costs should be reviewed. | 29 |
| 3.4 Standards and Templates Explains the need for consistency and standards in recording costs. | 30 |

#### 3.2 Collecting and Profiling Cost Data

| Purpose | In the Analysis of Outturn Costs, the project’s costs that have been developed through previous cost planning and control activities (see Planning and Control of Capital Costs, GN 2.2) are examined again in the light of final project costs. All information required for the analysis of final costs, should be defined and provided as clearly and efficiently as possible at this stage. Issues, assumptions and relevant research gathered from earlier analysis should be clearly presented. The Analysis of Outturn Costs report should explain what was expected and when, and it should set out any differences clearly and unambiguously. The goal is to assist future budgets to be adequate to deliver proposed facilities in a fully functioning condition. |
| --- | --- |

| Scope | The cost analysis element of the project review on completion should examine; Contract Outturn Cost “Other” Costs The Final Outturn Cost for a Contract can be defined as the Contract Sum adjusted in accordance with the terms of the Contract including Change Orders and Compensation Events approved under the contract. The Sponsoring Agency should analyse the outturn costs of “other costs” outside of those related to the construction contract capital cost. These costs would include, but are not limited to, Professional Fees, Local Authority and other Utility Fees and Contributions and Site Acquisition. The guidance note Budget Development (GN 1.3) sets out the constituent parts of the Project Budget. In addition to the Construction Costs the Other Costs should similarly be categorized and tracked through the progress of the project culminating in completion as part of the Analysis of Outturn Costs. It is not intended to detail here the methodology and \ or format of such analysis. But the classification of Other Costs for similar projects (see Budget Development, Appendix A Budget Template for Building Projects and Appendix B Budget Template for Civil Engineering Projects) should be standardized across all sectors to facilitate inter-departmental comparisons. |
| --- | --- |

Continued on next page

3.2 Collecting and Profiling Cost Data, Continued

| Method | The Sponsoring Agencies should collect cost data in the format prescribed by the Sanctioning Authority. The format and presentation of the data required by CWMF guidance should be customised by the Sanctioning Authority to suit the various project sectors whilst also facilitating inter-agency cost comparisons. The Sanctioning Authority should regularly collate cost data received from the various agencies and generate national and sectoral cost profiles to aid the future cost planning of projects. The basic rules on how different costs are allocated to the various cost holding categories in a public works project during the Planning Stage continue to apply to the cost changes incurred at Implementation Stage. Such rules are necessary because when the basic cost data for one project is being compared with that of another it is important that the comparison is being made on like-for-like basis. However, before such comparisons are made it may be necessary to make some adjustments to the data to deal with factors such as proportionality (i.e. quantity), location, quality and price. At the end of this process the resultant cost information forms the benchmark material that is used in the development of budgets at a very early stage (i.e. appraisal stage) for new projects. |
| --- | --- |

| Maintaining Historical Cost Data | Sanctioning Authorities that have multi-annual capital investment programmes have developed national cost limits/norms in their sectors for various types of repeat projects. These cost limits/norms are updated at regular intervals to take account of changes that may have arisen during the intervening period and also to reflect projected construction inflation. The type of changes that can arise during the intervening period might be: revision to output functional requirements due to changes in the service delivery requirements; changes to quality and standard of requirements; or legislative changes (e.g. VAT, environmental provisions/restrictions, fire safety requirements). Should such changes arise in the intervening period then it may be necessary to introduce them into a project during the construction stage. The capture of cost data associated with these changes in such circumstances is very useful in determining how much the cost limit/norm should be adjusted at the next revision date to take account of these changes. Also it is important to know what particular cost holding categories have been affected and the extent to which they have been affected by the changes. |
| --- | --- |

#### 3.3 Analysis of Additional Construction Cost

| Costs under examination | The additional costs under examination in this guidance note are those that are extra at project completion to the amount set out in Article 3 of the Public Works Agreement the total of which is referred to as the final outturn costs. In order for all extra costs that arise during the construction period to be recoverable under the contracts they must be sanctioned by the Employers Representative (other than an arbitrator’s award). Strict notice periods must be observed for extra money to be recovered under the contract. Failure by the Contractor to observe these notice periods will result in forfeiture of any right to recovery. Therefore, the possibility of such events arising at completion stage should normally not arise as their resolution and approval should have been dealt with during the construction period. The only exceptions where cost events may only become evident at completion stage under the Public Works Contract are in the following circumstances: Time over-run when an extension has not been granted and where the Employer has deducted liquidated damages for the period after the Date for Substantial Completion; Employer set-off where the Employer exercises the right to deduct from amounts due or likely to become due to the Contractor sums that the Contractor owes to the Employer under the contract or under any contract; Price Variation is permitted on a project with a duration of more than 36 months from the Designated Date in accordance the Contract, or A dispute where there is an Arbitration award in accordance with the contract. Each of these circumstances is dealt with in detail in the guidance note Public Works Contracts (GN 1.5). |
| --- | --- |

| Final Cost | The final outturn costs have been defined as the summation of the initial Contract Sum as set out in Article 3 of the Public Works Contract Agreement and the sanctioned additional costs referred to above. It is important that both of these amounts are combined into an overall figure that represents the final outturn cost. However, in combining these figures consideration needs to be given: to integrating those cost events that are likely to repeat themselves on future projects into the appropriate standard cost holding categories established at tender cost analysis stage of the project. This is so the full cost of those cost holding categories are recorded for future reference. to record those cost events that are unique to a project in such a way that they are easily and separately identified in the future (if required). |
| --- | --- |

#### 3.4 Standard Approach to Cost Comparison

| Purpose | It is important that cost data being analysed is captured in such a way that it is capable of being re-used by different Sponsoring Agencies responsible for delivering capital works projects. To achieve this, a standard set of rules need to be put in place regarding how the costs of works should be attributed to each cost holding category in a project. The availability of good quality historical cost data is critical to forming a realistic estimated budget at appraisal stage on a capital project therefore it is essential that any cost analysis of outturn cost is correct and usable for future capital projects. It may be possible, of course, for a budget of a capital project to be beyond cost parameters acquired through analysis of outturn cost on previous similar projects. To this end it is important to note that information supplied through the analysis of outturn costs is not only a review of how a project performed in financial terms but also is merely a guide when planning future projects as some projects will have specific costs that are above and beyond typical cost parameters. |
| --- | --- |

| Classification and Coding of Work | To facilitate the implementation of a standard approach, and to maximize the benefit, it is imperative that the measurement of works is undertaken in accordance with an agreed method of measurement that is classified and coded into standard cost holding categories, whether it is building or civil works. The use of standard cost holding categories should be applied to all procurement types to enable cost profiles to be established and compared across the spectrum of procurement methods. In this regard Design and Build projects should require tenderers to submit a breakdown of their tender using the standard cost holding categories applicable to the project type. |
| --- | --- |

| Note Exceptional Costs | As mentioned previously, in a number of projects there will be instances whereby costs over and above the typical cost parameters will exist. It is therefore necessary to note the circumstances that cause such situations to arise. It is also necessary to identify separately the extra over costs associated with same. |
| --- | --- |

| Templates | There are two standard templates used for cost planning and control: one suitable for building projects (CO1), the other suitable for civil engineering projects (CO 2). Each form can also be used as a template for analysis of outturn costs at project review stage. |
| --- | --- |

### 4: Other Essential Review Activities

#### 4.1 Introduction

| Introduction | This chapter covers activities (other than Performance Evaluation) that are essential to complete the Project Review on Completion. |
| --- | --- |

| Topic | See Page |
| --- | --- |
| 4.2 Design Review Describes how the Design Brief becomes the foundation on which Design Review will be carried out. | 32 |
| 4.3 Analysis of Additional Construction Time Describes how additional construction time should be recorded and used for future reference. | 33 |
| 4.4 Value Management/Risk Management Review Describes how the contribution of Value Management and Risk Management should be analysed | 34 |

#### 4.2 Design Review

| Design Brief | The Design Brief is the full and completed statement of the Sponsoring Agency’s functional and operational requirements for a project. It defines all design requirements for a project including performance standards and quality thresholds. It is the foundation on which design will be developed and is the benchmark for measuring future design development. It is a factual record and a document of importance. It should form the basis of a post-project Design Review. |
| --- | --- |

| Structural Drawings / Schematics | The project handover process should ensure there are sufficiently detailed information and schematics to cover all deliverables. The Design Review should confirm: That information on design is available to the client in sufficient detail to satisfy ongoing maintenance and Health and Safety standards That detailed information on the design implemented corresponds to the original Design Brief requirements. Any lack of detail should be remedied and anomalies or contradictions resolved and recorded. |
| --- | --- |

| Design Review | The Design Review should pay particular attention to the following project parameters and record any lessons learned from experience: |
| --- | --- |

| Project Parameter | Review |
| --- | --- |
| Scope | The scope is to be checked to confirm that there has been no significant augmentation/change in the requirements or, if there is, that it is within acceptable limits. |
| Fitness for Purpose | The success of the design is assessed in line with client / user requirements. |
| Expected functional life | The expected functional life confirmed in the Design Brief is re-examined to verify that the functional life period for the facility has not changed. |
| Design Defects | Any apparent defects to be examined and recorded for action, resolution or future reference. |

#### 4.3 Analysis of Additional Construction Time

| Time under examination | The additional time under examination in this guidance note is the approved extra time after the Date for Substantial Completion in accordance with the Public Works Contract. In order for all extra time that arises during the construction period to be recoverable under the contract it must be sanctioned by the Employers Representative (having considered the use of the Programme Contingency) in accordance with the Contract. The Public Works Contract requires that strict notice periods be observed for extra time to be recovered under the contract. Failure by the Contractor to observe these notice periods will result in forfeiture of any right to recovery. Therefore, the possibility of such events arising at completion stage should normally not arise as their resolution and approval should have been dealt with during the construction period. Refer to Public This subject is dealt with in detail in the guidance note Public Works Contracts (GN 1.5). |
| --- | --- |

| Starting point | The overall time is the summation of the period for Date for Substantial Completion in accordance with the Public Works Contract, the sanctioned additional time referred to above and all other non-sanctioned time over-runs incurred during the construction period. It is important that all of these are combined into a single overall figure to represent an overall time that a project has taken to construct. This information may be useful in the planning of future projects in the following way: the construction period that should be included in consultants’ design and construction programmes and in main contract tender documents, especially if health and safety issues have given rise to the extra time incurred; and the tendering of construction related-services where a period has to be set for the construction stage in compliance with the Standard Conditions of Engagement. |
| --- | --- |

#### 4.4 Value Management and Risk Management Review

| Risk Management | Risk Management (RM) is an essential project management tool that is used to create the conditions for a successful project outcome. It should begin at the earliest stage in the project and continue throughout the project delivery lifecycle. Risks are events that may or may not occur, and they must be clearly distinguished from issues, which represent the realisation of risks despite the best efforts undertaken by the team to prevent them. When issues do occur, the team must change its focus from prevention to damage limitation. Both risks and issues cause project uncertainty and both need to be mitigated. It is good practice to have separate registers for risks and for issues. Guidance on what is required to implement Risk Management successfully is contained in Project Management (GN1.1). |
| --- | --- |

| Value Management | Value management (VM) is an essential project management tool, used to create the conditions for a successful project outcome. It should begin at the earliest stage in the project and continue throughout the project lifecycle. Effective use of value management requires a project team to consider the project and its environment in its entirety, rather than focusing strictly on technical issues. Value management contributes to achieving the best value for money. Guidance on what is required to implement Value Management successfully is contained in Project Management (GN1.1). |
| --- | --- |

| End-of-project review | Records of all VM and RM activities throughout the project should be examined in light of the final outcome and also the Risk and Issue Registers and Risk Management Plan should be reviewed. At this stage, uncertainties have been eliminated and assumptions have been confirmed as realistic or otherwise. Risks that had been quantified, with measures put in place to manage them, can be reassessed in light of actual events. The objective is to recover any information that would assist in developing strategies for future projects. |
| --- | --- |

#### Appendix: Template for End-of-Project Report Documents

| Project Title |  |
| --- | --- |

| Project Description |  |
| --- | --- |

| Sanctioning Authority |  |
| --- | --- |

| Sponsoring Agency |  |
| --- | --- |

| Reference (Tick ) | Design Review Value Management Report Risk Management Report Certificates of Execution Definitive Project Brief. |
| --- | --- |

a. Objectives of the Project

b. Purpose

c. Scope

Continued on next page

Appendix: Template for End-of-Project Report Documents, Continued

d. Project deliverables and/or outcomes

e. Performance

f. Issues

g. Governance and reporting requirements

i. Risk Management Strategies

j. Value Management Strategies

k. Project Execution Plan

Continued on next page

Appendix: Template for End-of-Project Report Documents, Continued

l. Functional Life of Facility

m. Design Review

o. Budget /Cost Review

p. Overall Construction Time

| Signed | __________________________________ Manager of Sponsoring Agency ________________________ Date |
| --- | --- |

# Footnotes

The current guidance note.

# Text boxes

Capital Works Management Framework

Guidance Note

Project Review on Completion

GN 4.1

Design and Build

Standard Conditions of Engagement

Capital Appraisal