Weather Events                                                                                                                                                                                                       Document Reference WE 1.0 V.1.0.                                                                                                                                                                                    28 July 2009

© 2009 Department of Finance

Published by: Department of Finance
Government Buildings
Upper Merrion Street
Dublin 2.

This document is not to be taken as a legal interpretation of the contracts or of the provisions governing public procurement. All parties must rely exclusively on their own skills and judgment or upon those of their advisors when making use of this document. The Government Construction Contracts Committee (GCCC), the National Public Procurement Policy Unit (NPPPU) and the Department of Finance and any other contributor to this guidance note do not assume any liability to anyone for any loss or damage caused by any error or omission, whether such error or omission is the result of negligence or any other cause. Any and all such liability is disclaimed.

#### Contents

1: Weather Events………………………………………………………………...11

  - Overview…………………………………………………………………………11

  - Weather Events in Public Works Contracts……………………………………...12

  - Met Éireann Weather Stations…………………………………………………...17

#### Foreword

| Purpose of this document | This document sets out the 90th percentile of past weather measurements for weather events described in the public works contracts (PW-CF1 to PF-CF7) as determined by Met Éireann. The data in this document should be used by practitioners when determining if an extension of time for a weather event under the public works contracts is warranted. |
| --- | --- |
|  | Note: the wording in PW-CF6 and PW-CF7 is slightly differently to the text above but means the same thing. Note:PW-CF8 does not specifically refer to weather events but can, if necessary, be addressed under Clause 1.1 Scope. |

| Data to be used in threshold calculations. | In determining the 90th percentile a weather station will not be used unless there are at least 10 years of data available in the last 12 years for each calendar month. Furthermore, Met Éireann uses all available data. This means that more data is used for long term weather stations. Also if data is not available for a given month, that month will simply be ignored in the calculations. Met Éireann quality control staff make estimates from time to time to fill small gaps in data, such estimates will be used in calculations. |
| --- | --- |

| Audience | This document is intended primarily for the guidance of Sponsoring Agencies embarking on capital works projects. It is also aimed at the project manager and external consultants responsible for drawing up tender documents. |
| --- | --- |

Continued on next page

Foreword, Continued

| What is the Capital Works Framework | The Capital Works Management Framework (CWMF) is a structure that has been developed to deliver the Government’s objectives in relation to public sector construction procurement reform. It consists of a suite of best practice guidance, standard contracts and generic template documents that form four pillars that support the Framework; the pillars are: A suite of standard forms of construction contracts and associated model forms, dispute resolution rules, model invitations to tender, forms of tender and schedules; The standard conditions of engagement for consultants, dispute resolution rules, model invitations to tender, forms of tender and schedules; Standard templates to record cost planning and control information; and for suitability assessment; and Extensive guidance notes covering the various activities in a project delivery process. |
| --- | --- |

Continued on next page

Foreword, Continued

| What is the Capital Works Framework (continued) | The content of the four pillars is outlined below. The constituent documents are coded according to the following scheme: Code Description Code Description PW-CF Public Works Contract Form COE Standard Conditions of Engagement MF Model Form GN Guidance Note AR Arbitration Rules CO Cost Planning / Control Form ITTS Invitation To Tender, Services ITTW Invitation To Tender, Works QC Questionnaire: Suitability Assessment for Service Provider QW Questionnaire: Suitability Assessment for Works Contractor FTS Form of Tender and Schedule GL Glossary WE Data on Weather Event |
| --- | --- |

| CWMF Pillar 1 | Public Works Contracts Contracts, Model Forms, Arbitration Rules, Invitations to Tender (works), and Forms of Tender & Schedules (works) Contracts PW-CF1 Public Works Contract for Building Works designed by the Employer PW-CF2 Public Works Contract for Building Works designed by the Contractor PW-CF3 Public Works Contract for Civil Engineering Works designed by the Employer PW-CF4 Public Works Contract for Civil Engineering Works designed by the Contractor PW-CF5 Public Works Contract for Minor Building and Civil Engineering works designed by the Employer PW-CF6 Public Works Short Form of Contract PW-CF7 Public Works Investigation Contract PW-CF8 Public Works Short Form of Investigation Contract PW-CF9 Public Works Framework Agreement Weather Events WE1.0 Met Eireann’s calculations of Weather Events |
| --- | --- |

Continued on next page

Foreword, Continued

| CWMF Pillar 1 (continued) | Model Forms MF 1.0 Model Forms (compendium of all model forms) MF 1.1 Bid Bond MF 1.2 Letter to Apparently Unsuccessful Tenderer MF 1.3 Letter of Intent MF 1.4 Letter of Acceptance MF 1.5 Letter to Tenderers Notifying Award MF 1.6 Performance Bond MF 1.7 Parent Company Guarantee MF 1.8 Novation and Guarantee Agreement MF 1.9 Appointment of Project Supervisor MF 1.10 Professional Indemnity Insurance Certificate MF 1.11 Collateral Warranty MF 1.12 Novation Agreement MF 1.13 Rates of Pay and Conditions of Employment Certificate MF 1.14 Bond – Unfixed Works Items MF 1.15 Retention Bond MF 1.16 Appointment of Conciliator MF 1.17 Bond – Conciliator’s Recommendation Arbitration Rules AR 1.0 Arbitration Rules Invitations to Tender (works) ITTW 1 Invitation to Tender for Works, Restricted Procedure ITTW 2 Invitation to Tender for Works, Open Procedure ITTW 3 Invitation to Tender, Investigation Contract under an Open Procedure Forms of Tender and Schedules FTS 1 Form of Tender and Schedule: Public Works Contract for Building Works designed by the Employer FTS 2 Form of Tender and Schedule: Public Works Contract for Building Works designed by the Contractor FTS 3 Form of Tender and Schedule: Public Works Contract for Civil Engineering Works designed by the Employer FTS 4 Form of Tender and Schedule: Public Works Contract for Civil Engineering Works designed by the Contractor FTS 5 Form of Tender and Schedule: Public Works Contract for Minor Building and Civil Engineering Works designed by the Employer FTS 6 Form of Tender and Schedule: Public Works Short Form of Contract FTS 7 Form of Tender and Schedule: Public Works Investigation Contract FTS 8 Form of Tender and Schedule: Public Works Short Form of Investigation Contract |
| --- | --- |

Continued on next page

Foreword, Continued

| CWMF Pillar 2 | Standard Conditions Standard Conditions of Engagement, Arbitration Rules, Invitations to Tender (services), and Forms of Tender & Schedules (services). Standard Conditions COE 1 Standard Conditions of Engagement for Consultancy Services (Technical) COE 2 Standard Conditions of Engagement for Archaeology Services Arbitration Rules AR 1.0 Arbitration Rules Invitations to Tender (services) ITTS 1 Invitation to Tender for Services, Restricted Procedure ITTS 2 Invitation to Tender for Services, Open Procedure Forms of Tender & Schedule (services) FTS 9 Form of Tender and Schedule, Consultancy Services (Technical) FTS 10 Form of Tender and Schedule, Archaeology Services |
| --- | --- |

| CWMF Pillar 3 | Cost Planning & Control / Suitability Assessment Cost Control & Planning Forms; and Suitability Assessment Forms for works and services. Cost Planning & Control Forms CO 1 How to Use the Costing Document (Building Works) Template CO 1.1 Costing Document (Building Works) CO 2 How to Use the Costing Document (Civil Engineering Works) Template CO 2.1 Costing Document (Civil Engineering Works, Roads) CO 2.2 Costing Document (Civil Engineering Works, Water Sector) CO 2.3 Costing Document (Civil Engineering Works, Marine) Suitability Questionnaires (works) QW 1 Questionnaire: Suitability Assessment for Works Contractor, Restricted Procedure QW 2 Questionnaire: Suitability Assessment for Works Contractor, Open Procedure QW 3 Questionnaire: Suitability Assessment for Works Specialist for specialist area Suitability Questionnaires (services) QC 1 Questionnaire: Suitability Assessment for Service Provider, Restricted Procedure QC 2 Questionnaire: Suitability Assessment for Service Provider, Open Procedure QC 3 Questionnaire: Suitability Assessment for Service Provider, Independent PSDP QC 4 Questionnaire: Suitability Assessment for Service Provider, Independent PSCS |
| --- | --- |

Continued on next page

Foreword, Continued

| CWMF Pillar 4 | Guidance Notes Guidance Notes GN 1.0 Introduction to the Capital Works Management Framework GN 1.1 Project Management GN 1.2 Project Definition and Development of the Definitive Project Brief GN 1.3 Budget Development GN 1.4 Procurement and Contract Strategy for Public Works Contracts GN 1.5 Public Works Contracts GN 1.6 Procurement Process for Consultancy Services (Technical) GN 1.6.1 Assessment of Construction Service Providers, Restricted Procedure GN 1.6.2 Assessment of Construction Service Providers, Open Procedure GN 1.7 Standard Conditions of Engagement, Guidance Note and Sample Schedules GN 2.1 Design Development Process GN 2.2 Planning and Control of Capital Costs GN 2.3 Procurement Process for Works Contractors GN 2.3.1 Assessment of Works Contractors, Restricted Procedure GN 2.3.2 Assessment of Works Contractors, Open Procedure GN 3.1 Implementation Process GN 4.1 Project Review Glossary GL 1.0 Glossary |
| --- | --- |

1. Weather Events

1.1 Overview

| Introduction | The public works contracts (PW-CF1 to PW-CF7) requires that the appropriate weather station nearest the site should be named in the Schedule in relation to recording weather measurements for the three weather events identified in the Contract which are: Precipitation Air temperature Wind speed Additional weather events may be added if required, however care needs be taken in selecting such events to ensure that the weather station chosen records the required measurements. It should also be noted that historical data for such events may not be published or even available from Met Éireann. Furthermore, a method of determining how the data is going to be used to determine if an extension of time is warranted will have to be devised by the Sponsoring Agency. |
| --- | --- |

| General considerations | Where most, or all, of construction activities on a project are executed outdoors, thy will be very sensitive to weather changes and therefore careful consideration must be given to both the planned duration of such a project and the weather events that are applicable under the contract for that project. |
| --- | --- |

| In this section | This section contains the following topics: |
| --- | --- |

| Topic | See Page |
| --- | --- |
| 1.2 Weather Events in Public Works Contracts Describes how weather events are calculated and the historical data used to determine entitlement to an extension of time | 12 |
| 1.3 Met Éireann Weather Stations | 17 |

1.2 Weather Events in Public Works Contracts

| Introduction | The reference in the Public Works Contracts (PW-CF1 to PW-CF5 - Schedule Part 1K) to weather measurements ‘... as determined by Met Éireann and published most recently...’ is the data published in this document. This data supplied by Met Éireann for publication is being published under the CWMF and it relates to the 90th percentile of past weather measurements for each month of the year measured at a particular location. This data will be reviewed periodically; however the frequency of such reviews will be at intervals of not less than five years and any Met Éireann updates will be published by way of revision to this document which is part of the CWMF. |
| --- | --- |

| Weather Event | A weather event under the Public Works Contracts is an event that, provided certain conditions are met, can allow a contractor extra time (arising out of delay due to bad weather) to complete the construction of a project without liquidated damages being deducted from the contractor’s payments because of the delay. Established 90th percentile weather thresholds for each month at particular weather stations based on historical data by Met Éireann for the three weather events identified in Schedule Part1K of PW-CF1 to PW-CF5 should be gauged against the contract weather measurements for a month to determine if relief for extra time is to be allowed. For extra time to be considered the 90th percentile for a particular event for a month will need to exceed the weather measurement for a month in the contract. The three events and the weather measurements for a month in the contract are: The number of days with rainfall exceeding 10mm; The number of days with a minimum air temperature less than 00 Celsius; and The number of days with maximum mean 10-minute wind speed exceeding 15 metres per second. The weather station that applies to a particular contract is indicated in Part1 K of the Schedule to the Contract. The tables that follow here show the thresholds for air temperature, precipitation and wind speed. It is envisaged that the three weather events referred to above will be the norm on most projects and that the thresholds in the tables that follow relate to those events; however, additional weather measurements may be added to this list for particular projects, if required. |
| --- | --- |

Continued on next page

1.2 Weather Events in Public Works Contracts, Continued

| Met Éireann’s calculations | The thresholds indicated in the tables below (from page 3) are derived by Met Éireann from historical data and are 90th percentile figures for each of the measurements in question. The definition of the 90th Percentile is: The 90th Percentile is the lowest value which has 90% of the sample less than or equal to it. In other words, this may be understood as expressing the notion that a given value was unusual in a 1-in-10 sense, based on actual historical weather conditions. The 90th percentile for a data series can be calculated as follows. 1 Given N sample of years 2 Order the data from lowest to highest. 3 Multiply N (the number of samples – years in this case) by 0.9. If this produces a whole number, the value corresponding to that number in the order is the 90th percentile. If 0.9 x N has a fractional part (as only whole numbers are possible), then the calculation will be by liner interpolation between the two nearest whole numbers selecting the lowest whole number that has 90% of the sample less than or equal to it. |
| --- | --- |

Continued on next page

1.2 Weather Events in Public Works Contracts, Continued

| Met Éireann’s calculations (continued) | As an example, look at Days with rainfall > 10mm for March at Valentia, for which there is data going back 67 years. In this case the data is sorted from lowest to highest – i.e. from 0 (the lowest) to 11 (the highest number of days with rainfall in excess of 10mm). So N = 67, and 0.9 x N = 60.3. The figure 60.3 falls between 7 and 8 days (i.e. between the 58th and 65th precentiles); so 8 is the lowest whole number which has 90% of the sample lower than it. Rainfall exceeded 10mm on this number of days… In this number of years… Subtotals* Percentile 0 8 8 12 1 10 18 27 2 13 31 46 3 7 38 57 4 7 45 67 5 5 50 75 6 5 55 82 7 3 58 87 8 7 65 97 9 0 65 97 10 0 65 97 11 2 67 100 *These are cumulative subtotals for the number of years with less than or equal to the number of days with rainfall in excess of 10mm. In this table, 7 days is in the 87th percentile, which is not sufficient for our purpose. But 8 days brings us over the 90% threshold – if March has 8 or more days of high rainfall, it would be considered unusual, as this has historically occurred in fewer than 1 in 10 years. |
| --- | --- |

Continued on next page

1.2 Weather Events in Public Works Contracts, Continued

| Air temperature thresholds | The following table shows the number of days on which the air temperature must fall below 0° Celsius (at named weather stations) in order for a weather event to be deemed to have occurred. For each contract (PW-CF1 to PW-CF5), part 1K of the Schedule indicates the weather station whose measurements apply. |
| --- | --- |

| Station | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ardee (Boharnamoe) | 17 | 17 | 13 | 10 | 6 | 0 | 0 | 0 | 2 | 6 | 11 | 15 |
| Ardfert (Liscahane) | 11 | 12 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 2 | 6 | 10 |
| Ardtarmon | 7 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 |
| Ballincurrig (Peafield) | 10 | 10 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 8 |
| Ballyshannon | 13 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 5 | 9 |
| Belmullet | 9 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 |
| Birr | 15 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 1 | 4 | 11 | 13 |
| Carron | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 8 |
| Casement Aerodrome | 14 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 4 | 11 | 11 |
| Connemara Nat. Park | 6 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 |
| Cork Airport | 11 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 |
| Derrygreenagh | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 1 | 5 | 12 | 16 |
| Dublin (Merrion Square) | 5 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 |
| Dublin (Phoenix Park) | 17 | 16 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 3 | 10 | 13 |
| Dublin Airport | 15 | 14 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 7 | 10 |
| Dungarvan (Carriglea) | 12 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 3 | 8 | 10 |
| Fermoy (Moore Park) | 16 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 1 | 4 | 10 | 14 |
| Fethard (Parsonshill) | 15 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 2 | 6 | 11 |
| Galway (Univ.Coll.) | 10 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 10 |
| John F. Kennedy Park | 11 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 6 | 10 |
| Johnstown Castle | 8 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 |
| Knock Airport | 12 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 |
| Maam Valley | 8 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 |
| Malin Head | 7 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 |
| Mount Russell | 8 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 4 | 11 |
| Mullingar | 17 | 19 | 13 | 8 | 1 | 0 | 0 | 0 | 0 | 5 | 10 | 16 |
| Shannon Airport | 13 | 15 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 8 | 10 |
| Sherkin Island | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 |
| Straide | 13 | 16 | 9 | 5 | 3 | 0 | 0 | 0 | 1 | 5 | 11 | 11 |
| Valentia Observatory | 7 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 |
| Warrenstown | 17 | 16 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 3 | 9 | 13 |
| Waterford (Tycor) | 10 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 |

Continued on next page

1.2 Weather Events in Public Works Contracts, Continued

| Precipitation thresholds | The following table shows the number of days on which precipitation must exceed 10mm (at named weather stations) in order for a weather event to be deemed to have occurred. For each contract (PW-CF1 to PW-CF5), part 1K of the Schedule indicates the weather station whose measurements apply. |
| --- | --- |

| Station | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ardfert (Liscahane) | 9 | 6 | 4 | 3 | 5 | 3 | 4 | 5 | 6 | 8 | 7 | 9 |
| Ardtarmon | 5 | 4 | 3 | 3 | 5 | 4 | 3 | 5 | 4 | 8 | 5 | 6 |
| Ballincurrig (Peafield) | 9 | 6 | 5 | 5 | 5 | 6 | 4 | 7 | 8 | 8 | 6 | 7 |
| Ballygar | 6 | 5 | 3 | 3 | 4 | 3 | 3 | 4 | 5 | 7 | 6 | 8 |
| Ballyshannon | 6 | 5 | 4 | 2 | 3 | 3 | 5 | 5 | 6 | 6 | 5 | 7 |
| Belmullet | 7 | 4 | 4 | 3 | 3 | 3 | 4 | 5 | 6 | 6 | 6 | 7 |
| Birr | 4 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | 4 | 6 | 4 | 4 |
| Carron | 10 | 9 | 8 | 5 | 6 | 5 | 4 | 8 | 7 | 10 | 8 | 12 |
| Casement Aerodrome | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 4 | 3 | 4 | 3 | 4 |
| Connemara Nat. Park | 9 | 9 | 7 | 6 | 7 | 5 | 5 | 9 | 7 | 10 | 9 | 11 |
| Cork Airport | 9 | 8 | 6 | 4 | 5 | 5 | 4 | 6 | 6 | 7 | 7 | 8 |
| Derrygreenagh | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 4 | 5 |
| Dublin (Merrion Square) | 3 | 3 | 2 | 3 | 3 | 4 | 3 | 3 | 4 | 4 | 4 | 4 |
| Dublin (Phoenix Park) | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 |
| Dublin Airport | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 4 | 4 |
| Dungarvan (Carriglea) | 9 | 6 | 5 | 5 | 5 | 5 | 5 | 7 | 6 | 8 | 8 | 8 |
| Fermoy (Moore Park) | 7 | 4 | 5 | 3 | 4 | 3 | 4 | 4 | 6 | 6 | 5 | 6 |
| Fethard (Parsonshill) | 4 | 3 | 3 | 3 | 4 | 5 | 3 | 6 | 5 | 6 | 5 | 6 |
| Galway (Univ.Coll.) | 7 | 5 | 5 | 4 | 5 | 4 | 4 | 5 | 6 | 8 | 7 | 8 |
| John F. Kennedy Park | 6 | 5 | 4 | 4 | 5 | 5 | 4 | 5 | 6 | 7 | 7 | 7 |
| Johnstown Castle | 8 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 7 | 7 | 6 |
| Knock Airport | 7 | 8 | 6 | 5 | 5 | 4 | 6 | 6 | 8 | 7 | 6 | 9 |
| Maam Valley | 18 | 16 | 13 | 9 | 10 | 9 | 8 | 13 | 11 | 14 | 16 | 17 |
| Malin Head | 5 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 6 | 6 |
| Mount Russell | 6 | 5 | 4 | 4 | 5 | 4 | 4 | 6 | 7 | 8 | 6 | 8 |
| Mullingar Ii | 5 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 6 |
| Shannon Airport | 5 | 4 | 3 | 3 | 3 | 4 | 3 | 4 | 5 | 5 | 5 | 6 |
| Sherkin Island | 7 | 6 | 6 | 5 | 6 | 3 | 4 | 5 | 6 | 7 | 7 | 8 |
| Straide | 9 | 7 | 5 | 3 | 5 | 3 | 2 | 5 | 5 | 7 | 7 | 8 |
| Valentia Observatory | 9 | 8 | 8 | 5 | 6 | 5 | 5 | 6 | 8 | 9 | 9 | 9 |
| Warrenstown | 4 | 4 | 3 | 3 | 3 | 5 | 3 | 4 | 4 | 5 | 4 | 5 |
| Waterford (Tycor) | 7 | 5 | 5 | 5 | 4 | 4 | 3 | 5 | 5 | 6 | 6 | 6 |

Continued on next page

1.2 Weather Events in Public Works Contracts, Continued

| Wind speed thresholds | The following table shows the number of days on which 10-minute wind speed must exceed 15 m/sec (29.16kt) (at named weather stations) in order for a weather event to be deemed to have occurred. For each contract (PW-CF1 to PW-CF5), part 1K of the Schedule indicates the weather station whose measurements apply. |
| --- | --- |

| Station | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Belmullet | 16 | 15 | 13 | 7 | 6 | 4 | 2 | 4 | 7 | 10 | 12 | 13 |
| Birr | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 |
| Casement Aerodrome | 13 | 12 | 11 | 3 | 3 | 1 | 1 | 2 | 4 | 8 | 9 | 11 |
| Cork Airport | 11 | 9 | 7 | 4 | 2 | 1 | 0 | 2 | 3 | 6 | 7 | 8 |
| Dublin Airport | 9 | 7 | 6 | 3 | 2 | 1 | 1 | 1 | 2 | 4 | 5 | 7 |
| Knock Airport | 6 | 9 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | 3 | 3 | 5 |
| Malin Head | 23 | 22 | 20 | 12 | 9 | 6 | 5 | 7 | 13 | 17 | 20 | 21 |
| Mullingar II | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 3 |
| Shannon Airport | 10 | 8 | 6 | 5 | 3 | 2 | 1 | 2 | 4 | 4 | 5 | 8 |
| Valentia Observatory | 10 | 7 | 6 | 4 | 2 | 1 | 0 | 1 | 2 | 5 | 7 | 9 |

1.3 Met Éireann Weather Stations

| Introduction | The weather stations listed below are stations for which data is available |
| --- | --- |

| Location of Weather Stations | Met Éireann’s main weather stations are located at: Belmullet Cork Airport Shannon Airport Casement Aerodrome Dublin Airport Valentia Osbervatory Malin Head Connaught Airport Mullingar |
| --- | --- |

| Precipitation levels and temperatures | In addition, precipitation levels and temperatures are recorded at the following locations: |
| --- | --- |

| County | Location |
| --- | --- |
| Clare | Carron |
| Cork | Fermoy (Moore Park), Sherkin Island, Ballincurrig |
| Donegal | Ballyshannon |
| Dublin | Phoenix Park, Merrion Square |
| Galway | NUIG, Maam Valley, Connemara National Park, Ballygar** |
| Kerry | Ardfert |
| Limerick | Mount Russell |
| Louth | Ardee* |
| Mayo | Straide |
| Meath | Warrenstown |
| Offaly | Derrygreenagh |
| Sligo | Ardfarmon |
| Tipperary | Fethard |
| Waterford | Waterford, Dungarvan |
| Wexford | Johnstown Castle, John F. Kennedy Park |

* Ardee may only be used for temperature purposes due to insufficient precipitation records.

** Ballygar may only be used for Precipitation purposes due to insufficient

temperature records

# Footnotes

The current guidance note.

The same weather events are referred in Clause 2.8 of PW-CF6, and Clause 4.6 of PW-CF7.

See Clause 2.8 of PW-CF6 and Clause 4.6 of CW-PF7

See Clause 2.8 of PW-CF6 and Clause 4.6 of CW-PF7

See Clause 2.8 of PW-CF6 and Clause 4.6 of CW-PF7

# Text boxes

Capital Works Management Framework

Weather Events

WE 1.0