- [Note to Employer: delete this text and replace with letterhead/print onto letterheaded paper]

- [Note to Employer: delete this text and replace with letterhead/print onto letterheaded paper]

- [Insert name and address of Contractor]

[Insert name of Contract]

[Insert date of Letter Agreement]

PUBLIC WORKS CONTRACTS - COVID-19 CO-OPERATION FRAMEWORK AGREEMENT

LETTER AGREEMENT

- Dear [         ],

- I refer to our recent discussions.

- Background

[insert name of Employer] has entered into a standard public works contract with [insert name of Contractor] dated [insert date of contract and, where applicable, list the date and title of any agreements supplemental to the contract made prior to the date of this letter agreement [including those for Site Closure costs under OGP guidance dated 14 April 2020]] (the ‘Contract’) to complete the Works (as defined in the Contract), which consist broadly of [insert description].

Under the document entitled ‘Roadmap for the Reopening of Society and Business’ published by Government on 1 May 2020, work on previously non-essential construction sites was permitted to re-commence from 18 May 2020.  The Return to Work Safely Protocol (the ‘Protocol’), published on 9 May 2020, has been developed by the Department of Business, Enterprise and Innovation and the Department of Health in consultation with the Labour Employer Economic Forum. The Protocol provides the operative guidance for the introduction of measures necessary in the workplace, including construction sites, to reduce the risk of spreading Covid-19 (‘Protocol Measures’). The Employer considers that the Contract does not provide an entitlement to the Contractor to an extension of time or to recover any costs associated with implementing the Protocol Measures.

On foot of the Protocol Measures, the Office of Government Procurement (‘OGP’) issued a guidance note (dated 24 June 2020) (‘Framework Note’) encouraging the parties to a public works contract to undertake a proactive and collaborative approach, within existing budget constraints, to address issues as they arise in relation to the implementation of the Protocol Measures to help ease the financial burden on contractors.

As the Contract was entered into on or before 14 April 2020 and the site was closed from 28 March 2020 and permitted to re-open from 18 May 2020, in line with the Framework Note, the Employer’s Representative, with the consent of the Employer, invited the Contractor to an exploratory meeting for the purpose of reviewing the impact of the Protocol Measures on the Works. The Parties have concluded one or more exploratory meetings and the Contractor has accepted the invitation from the Employer to participate in the Covid Co-operation Framework.

The Parties have agreed as set out in this letter agreement (the ‘Supplemental Letter’) to engage with one another on an on-going and without prejudice basis during the Applicable Period to determine the extent to which the Works, or elements of the Works, are impacted and to seek to agree in accordance with Framework Note, a grant of Ex Gratia Relief (as later defined).

By our signature, and by your countersignature, of this Supplemental Letter (and the return to me of the signed counterpart), now it is hereby agreed as follows in consideration of the mutual agreements set out below (and for other good and valuable consideration the receipt and sufficiency of which is acknowledged by each of the Parties):

Definitions

In this Supplemental Letter (including the recitals) and in the Covid Notice (later defined), unless the context otherwise requires (and unless otherwise defined in this Supplemental Letter), terms and expressions used herein shall have the same meaning as in the Contract.

In this Supplemental Letter:

- ‘Applicable Period’ means the period commencing on the date of this Letter Agreement and ending on the expiry of two weeks written notice of termination (given in accordance with Clause 4.14 of the Contract) by either party to the other party.

- ‘Ex Gratia Extension of Time’ means the period in respect of which the Employer ex gratia waives voluntarily the application of liquidated and ascertained damages otherwise applicable under the Contract in respect of delay in completion of the Works due to implementation of the Protocol Measures, as envisaged in the Framework Note.

- ‘Ex Gratia Payment’ means the ex gratia payment by the Employer of an amount in respect of a contribution by the Employer to the reasonable, unavoidably incurred and vouched direct costs due to implementation of the Protocol Measures, as envisaged in Section A4 of the Framework Note.

- ‘Ex Gratia Relief’ means relief agreed to be granted to the Contractor comprising one or more of both an Ex Gratia Extension of Time and an Ex Gratia Payment.

Each of the Parties represent and warrant to the other Party that:

it has obtained all authorisations, consents, approvals, resolutions, licences, exemptions, filings, notarisations or registrations required to enable it to lawfully enter into and implement this Supplemental Letter and that all such authorisations are effective and in full force and effect at the date of this Supplemental Letter; and

it has the requisite power to enter into and perform and deliver its obligations and covenants contained within this Supplemental Letter.

The Contractor represents and warrants to the Employer as follows:

insofar as requested by the Employer (and/or by the party nominated by the Employer to act on its behalf for the purposes of arriving at the Ex Gratia Relief) to do so, will during the Applicable Period:

provide a complete and full break-down, on a transparent and ‘open book’ basis, of both (a) the Contract preliminaries and/or rates in the Pricing Document and (b) the Contractor’s unavoidably incurred and vouched direct costs of implementing the Protocol Measures;

furnish a programme which complies with Clause 4.9 of the Contract;

furnish progress reports in accordance with Clause 4.10;

make all its records, supporting and vouching material available; and

provide such other information as the Employer’s Representative requests,

- in either case, to the Employer or to the party nominated by the Employer;

it has not claimed, as part of the make-up of the Ex Gratia Relief, any cost in respect of which it has received assistance through the Temporary Covid-19 Wage Subsidy Scheme operated by the Office of the Revenue Commissioners;

the Surety providing the Performance Bond, where a Performance Bond is required by the Contract, and/or the guarantor providing a guarantee, where a guarantee is required by the Contract, has consented to this Supplemental Letter and the Contractor has furnished evidence in a form reasonably satisfactory to the Employer of such consent;

the Contractor remains compliant with its obligations in connection with the payment of taxes;

the Contractor remains compliant with its obligations under the Contract.

Where the Contractor has, prior to the date of this Supplemental Letter, submitted or where subsequent to the date of this Supplemental Letter, the Contractor submits, a claim in accordance with sub-clause 10.3 of the Contract that relates to the implementation of Protocol Measures (the ‘Protocol Measures Claim’), the Employer’s Representative shall pause the determination process under the Contract on the Protocol Measures Claim, subject to the outcome of the process in the Covid Co-operation Framework such that, from the date of execution by both the Employer and the Contractor of this Supplemental Letter, the determination of any such Protocol Measures Claim by the Employer’s Representative under the Contract will be deferred until the notice to withdraw by either party from the Covid Co-operation Framework.

Unless the Protocol Measures Claim has been, subsequent to the date of this Supplemental Letter, withdrawn and waived by the Contractor in writing, then in the event that either party provides a notice to withdraw from the Covid Co-operation Framework, such Protocol Measures Claim shall be treated, for the purpose of compliance with notice requirements under Clause 10.3 of the Contract, as having been submitted on the next working day falling after the date notice to withdraw was issued.

The Parties shall engage with each other in the manner provided in the Framework Note. During the Applicable Period, if the Parties agree for any period the amount of the Employer’s contribution to any reasonable, unavoidably incurred and vouched direct costs incurred by the Contractor due to implementation of the Protocol Measures, as envisaged in the Framework Note and/or any time implications (apportioned in line with the burden sharing principles in the Framework Note), the Employer’s Representative shall issue a notice (the ‘Covid Notice’) to both the Employer and the Contractor in the form of the Model Form attached in Appendix One hereto. The Covid Notice shall set out, subject to the terms and conditions of this Supplemental Letter, the extent of the Ex Gratia Relief for the period identified in the Covid Notice.

- Provided both the Employer and the Contractor shall each have signed the Covid Notice to signify their agreement with its contents, and the Contractor shall have returned a signed counterpart to the Employer, the Ex Gratia Payment shall be paid by the Employer with the next scheduled interim payment due under the Contract following the date of the receipt by the Employer of the signed counterpart of the Covid Notice save where the Employer is entitled under the Contract to withhold any payment otherwise due in whole or in part to the Contractor, in which case the Ex Gratia Payment shall not be payable to the extent of the amount of the withholding. The Ex Gratia Payment shall not be included in a certificate of the Employer’s Representative and shall not be subject to retention. The Contractor waives any claim and/or entitlement to interest for late payment of the Ex Gratia Payment. The aggregate of any Ex Gratia Extensions of Time set out in any Covid Notice shall be applied by the Employer to any calculation of liquidated damages after the Employer’s Representative has issued the certificate of Substantial Completion under the Contract.

The decisions of the Employer relating to Ex Gratia Relief, including the amount and make up of it, are final and binding on the Parties. It is acknowledged by the Contractor that, in the event that the Contractor is in breach of any of its commitments made in this Supplemental Letter and/or if any of the warranties and/or representations given by the Contractor in this Supplemental Letter are incorrect or untrue, the Employer has the right to a refund of the Ex Gratia Payment and to withdraw any Ex Gratia Extension of Time already agreed.

The execution of this Supplemental Letter:

by the Employer, is without its admitting or otherwise accepting that it has any responsibility under or in connection with the Contract for any costs, or for granting any extension of time in respect of delays, associated with implementing the Protocol Measures, and

does not alter either Party’s rights, duties or obligations under the Contract and shall not be used as a precedent.

If the Contractor makes any Protocol Measures Claim under the Contract or otherwise against the Employer in connection with the Protocol Measures, and is successful in such claim, the amount payable and/or the extension of time due to the Contractor as a consequence of such Protocol Measures Claim shall be reduced by the amount of the aggregate of the Ex Gratia Payments and the Ex Gratia Extension of Times respectively. In the event the aggregate of the Ex Gratia Payments exceeds the amount determined as due to the Contractor in connection with such Protocol Measures Claim, the Contractor shall pay to the Employer the amount of such excess within ten days of such amount being demanded. In the event the aggregate of the Ex Gratia Extensions of Time exceeds the extension determined as due to the Contractor in connection with such Protocol Measures Claim, the Employer shall be entitled to withdraw the period of such excess upon notice to the Contractor.

This Supplemental Letter may be executed in any number of counterparts, each of which when executed will constitute an original but all of which together shall constitute the same instrument.

The Contract, this Supplemental Letter and any Covid Notices as signed by both Parties shall together constitute the entire agreement between the Parties with respect to the Protocol Measures and each of the Parties acknowledge to the other Party that they have not been induced to enter into this Supplemental Letter by any statement or promise except to the extent expressly set out in this Supplemental Letter.

No provision in this Supplemental Letter shall be deemed waived, amended or modified by a Party, unless such waiver, amendment or modification is made in writing and signed by the Parties hereto.

Save to the extent that it is supplemented by this Supplemental Letter, the Parties agree that the Contract shall continue in full force and effect.

This Supplemental Letter shall be governed by and construed in accordance with the laws of Ireland and the Parties hereto submit to the exclusive jurisdiction of the Irish courts for the resolution of disputes hereunder.

Please sign where indicated below to acknowledge your acceptance of, and agreement to, the foregoing.

Yours sincerely

_____________________

for and on behalf of [insert name of Employer].

[insert name]

[insert role]

By signing below, we acknowledge and agree to the terms of this Supplemental Letter.

_____________________

for and on behalf of [note to Employer: insert name of Contractor].

NAME:

TITLE:

[On the headed notepaper of the Employer's Representative]

APPENDIX ONE: COVID NOTICE

To each of:

the Employer: [Insert name and address of Employer]; and

the Contractor: [Insert name and address of Contractor]

Project: [Insert project description]

Contract: [Insert date of Contract]

Supplemental Letter: [Insert date of Supplemental Letter]

Date of this Covid Notice: [Insert date]

This is a COVID NOTICE issued in accordance with, and subject to, the Supplemental Letter in respect of the period between

18 May 2020 and [Insert date at end of first period covered]

[OR (Note to ER: delete preceding or following date range as appropriate)]

[Insert date at start of subsequent period covered (Note to ER: the start date of a subsequent period will be the day after the last date of the prior Covid Notice)] and [Insert date at end of subsequent period covered] (‘this Period’).

The reasonable, unavoidably incurred and vouched direct costs due to implementation of the Protocol Measures in this Period has been calculated at €[Insert figure (if none agreed, insert 'Nil')] and the amount of the Ex Gratia Payment agreed to be paid by the Employer is €[Insert figure (if none agreed, insert 'Nil')].

The period in respect of which liquidated and ascertained damages would otherwise be applicable under the Contract in respect of delay in completion of the Works due to implementation of the Protocol Measures in this Period is [Insert number of days (if none agreed, insert 'Nil')] and the Ex Gratia Extension of Time is [Insert number of days (if none agreed, insert 'Nil')] Site Working Days.

The Parties acknowledge that they have not been induced to signify their agreement to this Covid Notice by any statement or promise except to the extent expressly set out in this Covid Notice.

Signed:________________________________________

EMPLOYER’S REPRESENTATIVE

By signing below, you acknowledge and agree to the terms of this Covid Notice.

Employer

_____________________

for and on behalf of [Note to ER: insert name of Employer]

NAME:

TITLE:

DATE:

Contractor

_____________________

for and on behalf of [Note to ER: insert name of Contractor]

NAME:

TITLE:

DATE:

in the form of any of PW-CF1-PW-CF5.